## Hoja1
Milestones (per week) - 7 weeks!
Responsable | Task | Friday
Michael | Project proposal - Edition & Research | 2015-10-16
Krista | Project proposal - Edition & Research
Dustin | Project proposal - List of app requirements, definition of technical implementation
Eli | Project proposal - List of app requirements, interface design
Maryi | Project proposal - List of app requirements, interface design
Michael | Literature review | 2015-10-23
Krista | Literature review
Dustin | Website set-up on GitHub
Eli | Database design and initial implementation
Maryi | Ethics & project evaluation methodology - interface design
Michael | Documentation of user requirements and app implementation | 2015-10-30
Krista | Documentation of user requirements and app implementation
Dustin | App website implementation
Eli | Database implementation
Maryi | Ethics & project evaluation methodology - design of user evaluation
Michael | Documentation of app implementation | 2015-11-06
Krista | Documentation of app implementation
Dustin | Connection database-webapp
Eli | Connection database-webapp
Maryi | Web app testing and reports
Michael | Documentation of app implementation | 2015-11-13
Krista | Documentation of app implementation
Dustin | Connection database-webapp
Eli | Connection database-webapp
Maryi | Conduct user evaluation
Michael | Documentation of user feedback & literature research | 2015-11-20
Krista | Documentation of user feedback & literature research
Dustin | Implementation of changes based on user feedback
Eli | Implementation of changes based on user feedback
Maryi | Implementation of changes based on user feedback
Michael | Documentation of user feedback & literature research | 2015-11-27
Krista | Documentation of user feedback & literature research
Dustin | Implementation of changes based on user feedback
Eli | Implementation of changes based on user feedback
Maryi | Web app testing and reports - version 2.0
Michael | Project final report - Edition & final contributions | 2015-12-04
Krista | Project final report - Edition & final contributions
Dustin | Preparing app demo- last fixes
Eli | Preparing app demo- last fixes
Maryi | Preparing app demo- last fixes